## Plan
PSP Time Recording Log
Student | Wesley
Program | Company on Chrome using Angular
Language | Javascript - Angular
Instructor | Lu Feng
Date | 2017-04-07
Project | Phase | Date | Start | Int Time | Stop | Delta Time | Comments
PSP 2 | Planning | 2017-04-07 | 10:00 | 0:00 | 10:15 | 0:15 | Check PSP3 requirements
| Analysis | 2017-04-07 | 10:15 | 0:00 | 10:30 | 0:15 | Check classes that need to be modified
| Design | 2017-04-07 | 10:30 | 0:00 | 10:45 | 0:15 | Create functions needed in model that need to be used
| Coding | 2017-04-07 | 10:45 | 0:00 | 11:00 | 0:15 | Code changes
| Testing | 2017-04-07 | 11:00 | 0:00 | 11:15 | 0:15 | check model in console.log
| Planning | 2017-04-07 | 11:15 | 0:00 | 11:30 | 0:15 | Check product file needed for product input
| Analysis | 2017-04-07 | 11:30 | 0:00 | 11:45 | 0:15 | Copy SalesPerson file input and see what needs to change
| Design | 2017-04-07 | 11:45 | 0:30 | 13:00 | 0:45 | Check how existing code interacts with copied code
| Coding | 2017-04-07 | 13:00 | 0:00 | 13:30 | 0:30 | Change Product related code to use file input and format correctly
| Testing | 2017-04-07 | 13:30 | 0:00 | 13:45 | 0:15 | Run index file and check results
| Planning | 2017-04-08 | 10:00 | 0:00 | 10:30 | 0:30 | What angular features to add
| Analysis | 2017-04-08 | 10:30 | 0:00 | 11:00 | 0:30 | check angular features that can be implemented
| Design | 2017-04-08 | 11:00 | 0:00 | 11:30 | 0:30 | Check how the angular features react with existing code
| Coding | 2017-04-08 | 11:30 | 0:30 | 13:00 | 1:00 | Add features
| Testing | 2017-04-08 | 13:00 | 0:00 | 13:15 | 0:15 | Run index file and check results
| Planning | 2017-04-08 | 13:15 | 0:05 | 13:30 | 0:10 | Adding a factory to contain the model
| Analysis | 2017-04-08 | 13:30 | 0:00 | 13:45 | 0:15 | How the classes react with the model
| Design | 2017-04-08 | 13:45 | 0:15 | 14:30 | 0:30 | How to implement
| Coding | 2017-04-08 | 14:30 | 0:00 | 15:00 | 0:30 | Implement changes
| Testing | 2017-04-08 | 15:00 | 0:00 | 15:15 | 0:15 | Check index file and make sure the model can still run
7:40
Formulas:
Date = [Date, row above]

## Actual
PSP Time Recording Log
Student | Wesley
Program | Company on google chrome
Language | Javascript - Angular
Instructor | Lu Feng
Date | 2017-05-05
Project | Phase | Date | Start | Int Time | Stop | Delta Time | Comments
PSP2 | Planning | 2017-05-05 | 10:00 | 0:00 | 10:05 | 0:05 | Check PSP3 requirements
| Analysis | 2017-05-05 | 10:05 | 0:00 | 10:10 | 0:05 | Check classes that need to be modified
| Design | 2017-05-05 | 10:10 | 0:00 | 10:15 | 0:05 | Create functions needed in model that need to be used
| Coding | 2017-05-05 | 10:15 | 0:00 | 10:25 | 0:10 | Code changes
| Testing | 2017-05-05 | 10:25 | 0:00 | 10:30 | 0:05 | check model in console.log
| Planning | 2017-05-05 | 10:30 | 0:00 | 10:35 | 0:05 | Check product file needed for product input
| Analysis | 2017-05-05 | 10:35 | 0:15 | 11:00 | 0:10 | Copy SalesPerson file input and see what needs to change
| Design | 2017-05-05 | 11:00 | 0:00 | 11:15 | 0:15 | Check how existing code interacts with copied code
| Coding | 2017-05-05 | 11:15 | 0:00 | 11:45 | 0:30 | Change Product related code to use file input and format correctly
| Testing | 2017-05-05 | 11:45 | 0:00 | 11:50 | 0:05 | Run index file and check results
| Planning | 2017-05-05 | 11:50 | 0:00 | 12:15 | 0:25 | What angular features to add
| Analysis | 2017-05-05 | 12:15 | 0:00 | 12:30 | 0:15 | check angular features that can be implemented
| Design | 2017-05-05 | 12:30 | 0:00 | 12:45 | 0:15 | Check how the angular features react with existing code
| Coding | 2017-05-05 | 12:45 | 0:00 | 13:30 | 0:45 | Add features
| Testing | 2017-05-05 | 13:30 | 0:00 | 13:35 | 0:05 | Run index file and check results
| Planning | 2017-05-05 | 13:35 | 0:00 | 13:45 | 0:10 | Adding a service to contain the model
| Analysis | 2017-05-05 | 13:45 | 0:00 | 13:50 | 0:05 | How the classes react with the model
| Design | 2017-05-05 | 13:50 | 0:00 | 14:00 | 0:10 | How to implement
| Coding | 2017-05-05 | 14:00 | 0:00 | 14:30 | 0:30 | Implement changes
| Testing | 2017-05-05 | 14:30 | 0:00 | 14:45 | 0:15 | Check index file and make sure the model can still run
Formulas:
Date = [Date, row above]

## Instructions
Time Recording Log Instructions
General | - Record all of the time you spend on the project.
- Record the time in minutes.
- Be as accurate as possible.
- If you need additional space, use another copy of the form.
- If you forget to record the starting, stopping, or interruption time for an activity, promptly enter your best estimate.
Header | - Enter your name and the date.
- Enter the program name and number.
- Enter the instructor’s name and the programming language you are using.
Project | Enter the program name or number.
Phase | Enter the name of the phase for the activity you worked on, e.g. Planning, Design, Test.
Start Date and Time | Enter the date and time when you start working on a process activity.
Interruption Time | - Record any interruption time that was not spent on the process activity.
- If you have several interruptions, enter their total time.
- You may enter the reason for the interrupt in comments.
Stop Date and Time | Enter the date and time when you stop working on that process activity.
Delta Time | Enter the clock time you actually spent working on the process activity, less the interruption time.
Comments | Enter any other pertinent comments that might later remind you of any unusual circumstances regarding this activity.